## Cover Sheet
Acronyms EPC - Engineering, procurement, and construction firm ESB - Electric school bus OEM - Original equipment manufacturer RFI - Request for information RFP - Request for proposals STEAM - Science, Technology, Engineering, the Arts, and Mathematics TCO - Total cost of ownership
School Bus Electrification - Template Roadmap
December 2022
This Template Roadmap is meant to accompany WRI's Step-by-Step Guide to School Bus Electrification (click anywhere on this text box; URL in first row of Template Roadmap tab), a resource for school bus electrification that identifies common steps for electrifying a school bus fleet and how to center equity in that process. This template roadmap can be used as a project management tool to visualize various timelines, identify which steps can occur in parallel and which should be done sequentially, and the overlap of multiple workstreams. Primary users of this tool will likely be transportation directors, (assistant) superintendents, business managers or external consultants, however it may be useful for a variety of project actors.
The transition to electric school buses typically follows a general roadmap (see image below) and can take around two years of planning before the first buses hit the road, with full fleet transition spanning additional years depending upon the size of the fleet and the pace of the transition. This Roadmap is meant to offer a sample for best case project execution. Exact timing and steps will depend upon bus ownership, local capacity, internal processes, financing and funding, facility upgrade needs, local grid capacity and the availability of buses and chargers, so the "Template Roadmap" tab should be adjusted to align with district-specific timelines and needs. The "Template Project Management" tab offers each step broken out.
Each step presents opportunities to center equity in the process and outcomes. This equity-oriented approach is critical to ensure that the transition to electric school buses helps address, rather than reinforce, long-standing inequities in transportation, education and other systems. School districts should engage the full range of impacted stakeholders from the very beginning of the project to co-develop a roadmap with defined equity strategies. Within the planning stages, school districts can integrate equity considerations when choosing which facilities to upgrade and routes to electrify, ensuring the benefits of this new technology go to the communities that need them most. During procurement, school districts can expand the impact of tax dollars by selecting vendors based on environmental and equity criteria and including community benefits like workforce development into contracts. Finally, school districts should identify desired outcomes and community benefits, for example, improved air quality and a reduction in greenhouse gas emissions, and then track and communicate progress.
This tool and accompanying step-by-step guide are designed from the perspective of a school district that owns and operates their bus fleet, but many steps will be the same for a district that contracts for bus service. Furthermore, electrification introduces new roles and responsibilities that can be assigned to existing or new partners, depending on the business model schools select. If a school district contracts out for transportation services, the contractor will likely be responsible for many of the steps. No matter the ownership and operations approach taken, it is important for school districts to understand their electrification needs and goals to make informed contracting decisions.
We welcome comments and suggestions for how to improve this resource. Please email ESBinfo@wri.org with your suggestions or to schedule a time to chat about ways to improve this resource.
Disclaimer: This template was developed by the Electric School Bus Initiative at World Resources Institute (WRI) based upon on-the-ground experience with transit and school bus electrification. More detailed methodology can be found online within the Step-by-Step Guide to School Bus Electrification. This template is intended to provide general guidance and should be used for informational purposes only. Any material in this template should be used at your own risk. WRI makes no warranties or representations about the completeness or accuracy of this information and assumes no responsibility for any consequences of your use of these materials. We recommend you consult your attorney, accountant and/or financial advisor to answer any financial, tax or legal questions.

## Template Project Management
Key
[5 empty] | User to enter one of these three terms in Column G | Completed
Underway
Delayed
Roadmap step | Sub-step | Responsible Party (Name, Title) Tasked with action completion | Secondary Party (Name, Org) To be consulted or informed | Start Date | Target Completion Date | Status | Notes
1. Foundation Setting | 1.1 Build and Educate Project Team
1.2 Engage Key Stakeholders
1.3 Research Funding and Financing Options
1.4 Create a Roadmap (based on this template) with Equity Strategies
2. Charging Infrastructure and Operations Planning | 2.1 Conduct Facility Assessment
2.2 Develop Charging Infrastructure Plan
2.3 Develop Operations Plan
3. Procurement and Installation | 3.1 Procure Buses and Other Services
3.2 Select and Procure Chargers
3.3 Upgrade Facilities and Install Electrical Infrastructure
4. Training, Testing and Deployment | 4.1 Train Drivers, Maintenance Workers and First Responders
4.2 Test Fleet and Equipment
4.3 Deploy Buses
5. Performance, Benefits and Scaling | 5.1 Monitor and Report on Performance and Benefits
5.2 Leverage Project for Learning and Other Impact
5.3 Update Your Roadmap and Scale

## Template Roadmap
Start Date (begin on the 1st of the month) | 2023-01-01
|  |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15 | Month 16 | Month 17 | Month 18 | Month 19 | Month 20 | Month 21 | Month 22 | Month 23 | Month 24 | Month 25 | Month 26 | Month 27 | Month 28 | Month 29 | Month 30 | Month 31 | Month 32 | Month 33 | Month 34 | Month 35 | Month 36
Roadmap Step | Sub-Step | Description | Resources and References | 2023-01-01 | 2023-02-01 | 2023-03-04 | 2023-04-04 | 2023-05-05 | 2023-06-05 | 2023-07-06 | 2023-08-06 | 2023-09-06 | 2023-10-07 | 2023-11-07 | 2023-12-08 | 2024-01-08 | 2024-02-08 | 2024-03-10 | 2024-04-10 | 2024-05-11 | 2024-06-11 | 2024-07-12 | 2024-08-12 | 2024-09-12 | 2024-10-13 | 2024-11-13 | 2024-12-14 | 2025-01-14 | 2025-02-14 | 2025-03-17 | 2025-04-17 | 2025-05-18 | 2025-06-18 | 2025-07-19 | 2025-08-19 | 2025-09-19 | 2025-10-20 | 2025-11-20 | 2025-12-21
1. Foundation Setting | 1.1 Build and Educate Project Team | Begin by building your core project team, establishing goals and a vision for fleet electrification and developing a base understanding of electric school bus technology and the market landscape. | WRI's Market Report and Buyer's Guide | 2023-01-01: Identify core project team (including utility) and their roles Schedule regular project team meetings Discuss project goals and priorities; 2023-02-01: Educate project team on electric school bus and charging technologies Assess market conditions and technology options Identify energy integration opportunities; 2023-03-04: If needed, hire a project manager to manage transition in house. Alternatively, include project management services within contracts for turnkey asset management, private fleet operators or other service providers.
| 1.2 Engage Key Stakeholders | Consult and collaborate on an ongoing basis with internal and external stakeholders who will be directly involved in project implementation and/or who will be impacted by fleet electrification, including school district employees, drivers, maintenance workers, utility staff, parents, students, teachers, community members who live near depots or charging infrastructure, and members of environmental justice or disability rights groups, particularly those that have been left out of past decision-making processes. | NAACP - Guidelines for Equitable Community Involvement | 2023-01-01: Identify internal and external stakeholders, how they might be impacted, and what benefits fleet electrification can provide; 2023-02-01: Work with communications team to develop communications materials like FAQs and lead discussions with external stakeholders Identify appropriate engagement methods depending on stakeholder group (e.g., survey, present at standing meeting, invitation to collaborate); 2023-04-04: Hold preliminary conversations to introduce stakeholders to your ESB project, understand their needs and concerns, and identify challenges and opportunities Discuss how and when to involve stakeholders going forward - for example, during planning for facility upgrades, route selection, and reporting out on indicators for project success Explore opportunities to move beyond "informing" or "consulting" community members (see "Resources and References" column); 2023-07-06: Hold check in with stakeholders when appropriate, potentially in tandem with Steps 2.2 and 2.3 when developing a charging and operations plan; 2024-01-08: Hold check in with stakeholders when appropriate, potentially in tandem with Step 5.1 when determining reporting plan; 2024-07-12: Hold check in with stakeholders when appropriate, potentially in tandem with Step 5.2 on public events; 2024-10-13: Hold check in with stakeholders when appropriate, potentially in tandem with Step 5.3 on updating your roadmap and equity strategies
| 1.3 Research Funding and Financing Options | Assess funding options available as well as financing that can help leverage the expected lifetime operating savings of ESBs to address upfront costs. Consider how new business models and financing options might enable electrification plans. | WRI's Business Models Blog, Guide & Directory (see Additional Resources at bottom of page for the Business Models Guide and School Bus Electric-as-a-Service (EaaS) Directory) | 2023-01-01: Evaluate potential business models, such as charging-as-a-service; 2023-02-01: Research federal and state funding opportunities; ask your electric utility about incentive programs Research potential revenue streams from environmental credits (e.g., low-carbon fuel standard credit markets) or from participation in utility programs (e.g., demand response); 2023-04-04: Run total cost-of-ownership (TCO) calculations
| 1.4 Create a Roadmap with Equity Strategies | Develop a roadmap (based on this template) as well as a vision for your ESB project, success factors, potential risks and actors, key steps and roles. Engage internal and external stakeholders. | Based on this template | 2023-01-01: Develop a fleet inventory Review other district roadmaps and fleet transition plans Connect with peer school districts for insights; 2023-03-04: Hold a road mapping work session or workshop (either internally or with key stakeholders, such as utilities and community groups) to identify key milestones, decision points, timelines and roles. Identify strategies to center and advance equity in your roadmap.; 2023-06-05: Share your draft roadmap with stakeholders to solicit input for modifications
2. Charging Infrastructure and Operations Planning | 2.1 Conduct Facility Assessment | Convene core project team to conduct a facility assessment and discuss the placement of chargers and any potential necessary upgrades to electrical infrastructure on the electric utility and/or the customer side of the meter. | VEIC/WRI's Electric School Bus Facility Assessment Guide | 2023-02-01: Convene project team to discuss project scale and considerations, such as 1) property ownership agreements and dynamics (if land is leased) and 2) scheduling necessary site assessments that take place in Month 5 of this sub-step; 2023-04-04: Conduct your own informal site assessment by taking photos (panel, site layout, etc.); send to electric utility Set up electric utility site assessment; 2023-05-05: Electric utility (engineering team) conduct formal site assessment - discuss potential electrical upgrades and associated costs for current and future deployments Identify easement procedures and requirements of all the utilities at your site (e.g., electric, water, sewer, gas, telecommunications, internet); 2023-06-05: Submit electric utility service or interconnection request (e.g., site image, single-line diagram, load letter); 2023-07-06: Bring in emergency responders to assess site for any required adjustments to accommodate ESBs
| 2.2 Develop Charging Infrastructure Plan | Begin planning for charging as early in the process as possible. Develop a strong relationship with your electric utility. Discuss electricity rates and managed charging with your electric utility. Hire external support, if needed. | VEIC/WRI's Working with Your Utilities Guide | 2023-01-01: Find meter number(s); share with electric utility to identify key or commercial accounts manager and establish electric utility relationship; 2023-02-01: Set up recurring meetings with electric utility (key or commercial accounts manager); 2023-03-04: Discuss with electric utility: -utility bill and expected changes -current and future rates (any electric vehicle-specific rates?) -interconnection processes and requirements ("make-ready" infrastructure coverage?) -"future proofing" mechanisms -how solar and stationary storage could complement fleet electrification and provide ancillary benefits to the district and community -potential to improve site energy efficiency and pursue other electrification projects; 2023-05-05: Acquire historic site electricity data from electric utility; 2023-06-05: Develop operations, charging infrastructure, and fleet transition plans (internally or using a consultant/engineering, procurement, and construction [EPC] firm) Engage internal and external stakeholders around plan details Incorporate as-built (final) drawings into your project plan as deliverables so that they can be referenced later with accurate depictions of the above-ground and underground infrastructure installed at the site; 2023-09-06: Conduct an equity review to identify potential risks or unintended consequences of the proposed plan
| 2.3 Develop Operations Plan | Develop a plan for associated operational shifts (e.g., route planning, parking arrangement and charging schedules). Consider beyond your first deployment. |  | 2023-02-01: Assess your current and anticipated fleet, routes and usages; 2023-03-04: If applicable (large project): consider hiring engineering, procurement, and construction (EPC) firm to facilitate electric utility relationship; gather quotes; select vendor; 2023-05-05: Identify the depots, routes and purposes best suited for initial ESB adoption, working with stakeholders that will be impacted by these changes
3. Procurement and Installation | 3.1 Procure Buses and Other Services | Decide if a Request for Information (RFI) or Request for Proposal (RFP) are necessary for ESB and/or management support. Work with procurement and business staff and district leadership. | WRI's Template RFI (https://electricschoolbusinitiative.org/request-information-rfi-template) and RFP (https://electricschoolbusinitiative.org/request-proposal-rfp-template) | 2023-03-04: Meet with your procurement and budget office; 2023-04-04: Arrange demonstrations or virtual meetings with OEMs/dealers/service providers; 2023-05-05: Develop draft RFI/RFP. Ensure favorable warranty terms and optional warranties are outlined; 2023-06-05: Develop and run an RFI and/or RFP (as needed) Considerations for final contract: warranties, maintenance, trainings for drivers and maintenance workers, requirements for local hiring or unionized labor, workforce development and more; 2023-10-07: Select vendor, with consideration to environmental and equity criteria Get approval from school board, city council, and community as needed; 2023-11-07: BUS: Issue purchase order/execute contract CHARGER: Make decision on charger brand and associated procurement processes; place order Consideration: -Implications of asset ownership (e.g., California's Low Carbon Fuel Credits are issued to the charger owner, not the party that owns the land); 2024-05-11: Staggered delivery of buses (ex: if place order for 10, schedule 2 per quarter, which allows for fewer delays in training, increased operator familiarity, and vehicle testing) Expect at least 6-9 months but prepare for 12-18 months depending on OEM, ESB type, backlog of orders, incoming demand from Clean School Bus Program, etc.
| 3.2 Select and Procure Chargers | Decide if an RFI/RFP are necessary for chargers, charge management software and/or a turnkey solution. Work with procurement and business staff and district leadership. |  | 2023-03-04: Check if your electric utility offers infrastructure incentives or programs (i.e., "make-ready") that would influence your charging decisions; 2023-04-04: Consider available business models, such as “charging-as-a-service”; 2023-05-05: Make decision on charger location, type (Level 2 or DC fast charger), quantity based on electric utility/ electrician/EPC firm recommendation Considerations: -Pursuing a phased approach may help balance immediate, mid- and long-range fleet electrification goals - Exploring what charging level meets fleet duty cycle - Level 2 may be able to meet the majority of fleet needs at a lower upfront price and total site upgrade cost -Aligning with procurement budget and site assessment; 2023-09-06: Review available chargers and their compatibility with your chosen buses, route planning, and "smart" chargers or those equipped with managed charging capabilities; 2024-03-10: Review third party charge management software solutions that give you the ability to remote control charging and notify you if there are issues; 2024-05-11: Coordinate with IT department on Wi-Fi implications for chargers
| 3.3 Upgrade Facilities and Install Electrical Infrastructure | Upgrade facility to accommodate new electrical infrastructure and/or parking and operations patterns. Consider additional energy efficiency upgrades or supporting clean energy projects, such as the installation of solar canopies. | WRI Video Series: All About Charing Infrastructure | 2023-03-04: Discuss ways to minimize upgrade costs through incentives, rebates, charger selection, and phased deployment up through the next five (5) years; 2023-04-04: Determine whether a procurement process will be needed for facility upgrades; run it if necessary; 2023-05-05: Evaluate the need for upgraded electrical infrastructure on both the electric utility (line) side and the site owner (load) side of the electric service meter; 2023-06-05: Obtain needed permits from local building authorities Bring in emergency responders to assess site for any required adjustments to accommodate ESBs; 2023-08-06: Appropriate parties (e.g., electric utility, hired contractor or other third party) break ground for necessary site construction and facility upgrades (in compliance with local codes) Considerations: -Not all charging decisions need to be finalized before beginning site upgrades. Building in elements of flexibility (e.g., installing service panel with expansion slots, conduit, and stub-outs but waiting on full charger build out beyond near-term [2-3 year] need) can help your district gain experience and adapt to unforeseen future challenges and needs.; 2023-12-08: Appropriate parties (e.g., electric utility, hired contractor or other third party) execute site construction and charger installation Considerations: -If able to use existing service/power, this could take anywhere between one (1) week and eight (8) months depending on complexity and size of project -If connecting new service is necessary (which depends on the number of chargers to be installed), this will likely take 12-18 months
4. Training, Testing and Deployment | 4.1 Train Drivers, Maintenance Workers and First Responders | Conduct appropriate trainings: -ESB 101 Basics: Drivers, mechanics, dispatch, front office staff -Drivers (basic safety, on/off, plug-in charging, maximizing efficiency) - Mechanics (advanced training, preventive maintenance, troubleshooting, diagnostics, understand high voltage elements while avoiding high voltage repair work as available through warranty) -First responder basics (dealing with an electric vs. internal combustion school bus, safety switches) as needed/requested by local firefighters, police, paramedics, etc. |  | 2023-04-04: Ask OEMs and dealers during meetings & demos about detailed training modules, number of hours, and after delivery support and training; 2023-05-05: Integrate detailed training for drivers and mechanics into RFP/RFI, purchase order, or contract specifying hours and people to be trained; 2023-12-08: Obtain bus safety and recommended maintenance documents from OEM or dealer; integrate into safety procedures; 2024-02-08: Train local inspectors; inquire whether the dealer/OEM can lead on this; 2024-03-10: Explore pre-delivery driver training options (e.g., train the trainer, test drive day); 2024-07-12: Timing of these next steps will vary based on delivery of buses (Step 3.1). Adjust accordingly. -------------------- Train drivers on: instrument clusters; regenerative braking; emergency high-voltage shutoff; charging practices; other key procedures; 2024-08-12: Train maintenance workers on: new electric components (e.g., electrically driven heating/cooling and power steering, volt meters, traction motors); preventative maintenance and schedules; diagnostics; proper high-voltage shutoff procedures; charger upkeep and maintenance; integrating vehicle telemetry with existing maintenance software; 2024-09-12: Train first responders on how to respond to emergency events Educate towing companies on options for transport and battery disconnect; 2024-10-13: Optional: Identify a lead trainer that will train incoming staff and be the fleet expert. They could receive additional training from OEM/dealer; 2025-02-14: Provide refresher training(s)
| 4.2 Test Fleet and Equipment | Examine and test all new equipment to ensure that it meets the specifications within your contract and procurement order and understand performance in real world conditions. |  | 2023-04-04: Obtain OEM spec sheets while meeting with dealers/OEMs for demos; 2023-05-05: Ensure that required specs are in the RFI/RFP draft for quotes Considerations: -Listing GPS data logger and telemetry services as a requirement; 2024-03-10: Design charging procedures and schedules; 2024-07-12: Timing of these next steps will vary based on delivery of buses (Step 3.1). Adjust accordingly. ------------------- Test your new buses on all proposed routes Test chargers and charging software Test telemetry and onboard operating; 2024-08-12: Work with dispatch and scheduling teams to adjust proposed route and charging plans based on test results
| 4.3 Deploy Buses | Finalize many of the same steps as an internal combustion bus, such as getting insurance and completing inspections. Update standard operating procedures, handbooks and safety protocols for ESB-specific needs. |  | 2024-03-10: Develop pre- and post-trip inspection checklist Conduct route planning and ESB assignment; 2024-04-10: Timing of these next steps will vary based on delivery of buses (Step 3.1). Adjust accordingly. ---------------------------------------- As ESBs arrive, complete standard bus commissioning procedures, such as numbering, obtaining permits and insurance, inspections, road testing etc. before using ESBs on student routes; 2024-07-12: Finalize/ confirm route planning based on testing performance Review warranty procedures; 2024-08-12: Begin operation of buses (after having properly trained staff)
5. Performance, Benefits and Scaling | 5.1 Monitor and Report on Performance and Benefits | Gather data to ensure that buses and chargers are functioning as expected and achieving maximum value. Identify outcomes to track based on the most important benefits to your school district and community. Identify methods for sharing these outcomes back with stakeholders, particularly those that you engaged in the process. |  | 2023-11-07: Determine who is responsible for: 1) compiling data on and tracking bus and charger performance 2) tracking and evaluating air quality, environmental, and other benefits; 2023-12-08: Develop a reporting plan, select indicators and establish your baseline, involving stakeholder input and aligning as much as possible with the metrics and process for diesel/gas/propane vehicles for easy comparison; 2024-09-12: Monitor telematics from buses, evaluate results, and make changes to operations as needed Track operating data, such as energy use, fuel economy (kWh/mi), state-of-charge, ambient temperature and cost savings Track maintenance costs and savings Track and evaluate air quality and environmental improvements Perform qualitative research and surveys to assess user experience and satisfaction with buses Share results to enable better research and support other school districts with fleet electrification
| 5.2 Leverage Project for Learning and Other Impact | Consider opportunities to develop Science, Technology, Engineering, the Arts and Mathematics (STEAM) curricula that involve ESBs for students or partner with workforce development programs or community colleges to help build a future pipeline of electric vehicle technicians. Communicate results and experience with elected officials, local advocates, the press and other school districts. |  | 2023-01-01: Engage students in community events, for example through a student sustainability or other relevant school organization Explore opportunities to integrate with local workforce development programs Share your experience with peer districts
[5 empty] | Reach out to communications team Work with communications team to develop a communications plan to engage your community | [12 empty] | Identify or develop a curriculum around ESBs for students |  |  |  | Timing of this step will vary based on delivery of buses (Step 3.1). Adjust accordingly. ---------------- Hold a ribbon-cutting for community leadership and partners; invite the press to attend |  |  | Hold an electric vehicle fleet day with other electric fleets in your area to share learnings
| 5.3 Update Your Roadmap and Scale | Move beyond an initial deployment. Explore alternative business models if necessary. |  | 2024-07-12: Work with your electric utility on managing peak consumption to avoid costly demand charges and grid-friendly siting of bus facilities
[20 empty] | Consider hiring a consulting firm/other entity for long-term fleet planning |  | Prepare a fleet replacement plan to understand how many ESBs to add each year, utilizing consultants as necessary |  |  | Discuss long term plans for charging infrastructure with electric utility and use modular installation for easy upgrades Update your roadmap and equity strategies based on stakeholder feedback from those involved in and/or impacted by the ESB project Consider alternative business models and service offerings in light of greater fleet electrification (refer to sub-step 1.3 "Research Funding and Financing Options") | [12 empty] | Discuss high voltage training needs and necessary personal protection equipment with OEM for post-warranty period
This template roadmap accompanies WRI's Step-by-Step Guide to School Bus Electrification. More detail on and resources for most steps can be found here: https://electricschoolbusinitiative.org/step-step-guide-school-bus-electrification